## Morix Client Web Application Te
Testing Env: http://147.93.155.211/ Testing credentials: Kunal@testing.com pass: Pass@5200
Module | Sub-module | Feature | TC & Scenario | Steps/Input data | Remarks | Testing(Pass/Fail)1 | Dev Remarks | Re-testing Remarks | Testing(Pass/Fail)2 | Testing(Pass/Fail)3 | Sanjay testing-status | Column1 | Column2
User & Role Management | User & Role management | Filters | To verify filters of team members Search | Searched by screen name and email | Search by name and email | Pass
User & Role Management | User & Role management | Filters | To verify filters of team members All Roles | Filter with drop-down selection by Client Admin | Filter with Client admin is working. | Pass |  | Filter working is fine but If super admin deactivate the sub-role from super admin then respective role should be removed from All roles drop-down list and Add new user- select role list. Also add a scroller for drop-down options list. | Fail
User & Role Management | User & Role management | Filters | To verify filters of team members All Status | Filter with drop-down selection status pending, apporved, rejected | Filter is working | Pass
User & Role Management | User & Role management | Filters | To verify of team members Created Date | Checked Created date filter | Checked, created date filter not found. inpute Required a created date filter column in team member listing table | Input |  | No changes for input | No change
User & Role Management | User & Role management | Add New User | To verify admin can add new team members successfully | Click on Add team member Add Profile picture, name, email, and phone | New team member added successfully. Please rename add new team member-to Add New User. as we following over all user & role management module. | Pass
User & Role Management | User & Role management | Add New User | To very the duplication of user | Add user with same details of existing user. | Error message shows when we try to add duplicated user. Please update it to text message. User alreday exiting. response- "message": "\nInvalid `prismaClinet_1.prisma.authUser.upsert()` invocation in\n/var/www/API/dist/src/Module/Admin/teams/controller.js:55:57\n\n 52 if (!req.body.id && password) {\n 53 insertData.password = (0, md5_1.default)(password);\n 54 }\n→ 55 let data = await prismaClinet_1.prisma.authUser.upsert(\nUnique constraint failed on the fields: (`email`)", | Fail | Done | A toast message added-User with email alreday exits | Pass
User & Role Management | User & Role management | Add New User | To verify the BASIC INFORMATION of team member | Are we adding profile picture to new team member? | There is no option to add profile picture of a new user | Fail | Not In Figma | Not in figma, But we added there a line, profile picture changes, so pls confirm that is it necessary or not. | No change
User & Role Management | User & Role management | Table | To verify Team member table column | checked table columns with respective figma | Input: Checked with compair to figma required to add a created date column in the table. | Input |  | No changes for input | No change
User & Role Management | User & Role management | Activate/Deactivate | To verify table action - activate/deactivate | Clicked on activate/deactivate button | Only Perfomed action to activate/deactivate, need to login and check with super admin where it should be show some validatio message if user deactivated | Testing Pending |  | Retested scenario: Created a new user with email mohdzubair204@gmail.com Activated the user. Logged in with the user account. Deactivated the user. Expected: A deactivated user should not be allowed to perform any activities or permissions. Actual: The deactivated user can still add, edit, and update their respective permissions. | Fail
User & Role Management | User & Role management | Resent Invite | To very resent invite to the user added | Resent Invite | Wrong toast message shown when we resent invite to the user Toast message response- - {"success":true,"message":"Credentials sent successfully","data":[]} its should be : Resent Invite Successfully | Fail | Done | Found Ok | Pass
User & Role Management | User & Role management | Edit | To verify table action - edit | Clicked on Edit button | Perfomed action edit. Failed to updated and Showing an error message as : "message": "\nInvalid `prismaClinet_1.prisma.authUser.upsert()` invocation in\n/var/www/API/dist/src/Module/Admin/teams/controller.js:55:57\n\n 52 if (!req.body.id && password) {\n 53 insertData.password = (0, md5_1.default)(password);\n 54 }\n→ 55 let data = await prismaClinet_1.prisma.authUser.upsert(\nUnique constraint failed on the fields: (`email`)", Inputs: Are we able to edit rejected user? | Fail | No Flow of Rejection Only Active and Inctive | Users are only activate and deactivated, no other flow found | No change
User & Role Management | User & Role management | Edit | To verify updated button should be availabe if user edit data | Click Select Role or removed role | When we removed the role, and select again then updated user button should be visible and allow to updated user. | Fail | No issue find | Rechecked with the new changes and found a new UI. Currently, when trying to edit a user by going to the Action → Edit option, the user fields are shown blank, and no data is displayed in the edit user form. UI: Pls add a scroller for Select Role field and add some pedding on cross remove button X. | Fail
User & Role Management | User & Role management | Sorting | To verify sorting for each table column | Checked by clicking on table column name | Input: No sorting filter found for table columns | Input |  | No changes for input | No change
User & Role Management | User & Role management | Pagination | To verify pagination of the table for team member | Checked by Rows per page:5,10,20,50,100 | Pagination is working with respective rows per pages | Pass
User & Role Management | User & Role management | Statistics | To verify Statistics of user & role menagement | Calculated TOTAL USERS, ACTIVE USERS, ADMIN USERS Checked statics | Inpute: we have statistics for Total User, Active User and Admin User. But we also having status pending, rejected | Input |  | New changes found as of now user can click on statistic and redirect and filter active, inactive and total users list. No changes for input, | Pass
User & Role Management | User & Role management | table | To verify checked and Unchecked All option in the table of team member | Clicked on Checked all option, and unchecked few team members on table list. | If we unchecked few users from table list then Checked All should be clear | Fail | is we uncheck few user it's showing - in the check box indicate Partial selection. It's inbuilt component Functionality | Ok got the comment | Pass
User & Role Management | User & Role management | User Permission | To verify that a user should be able to add and remove permissions. If a Super Admin removes a permission, then the user should be restricted from performing that action, such as View, Create, Edit, and Delete. | Go to Super admin-role manage, Select Role & Sub-Role, Checked by adding or removing permissions(Create, Edit, View and Delete) | Retesting | Pending |  | Retested, Not Working with respective permissions Create, Edit , View and Delete. Also note, 1. If super admin unchecked permission for create and View then also other permission should be unchecked automatically. 2. At Client login, we dont have view and Delete option but we have permission checkbox in super admin. | Fail
Media File Management | Media File Management | Search | To verify search by file name | File names | Search by file name working fine | Pass |  |  |  |  | Pass
Media File Management | Media File Management | Upload Media Files | To verify Upload Media Files with Upload Location | Four Media Uploaded(videos and Images) | Media uploaded and listed successfully | Pass |  |  |  |  | Pass
Media File Management | Media File Management | Move to folder | To verify media upload should be move to folders | Checked media and click on move to folder button | Media moved successfully | Pass |  |  |  |  | Pass
Media File Management | Media File Management | Single/ Multi Select Delete | To verify media listed, should be delete by single select or multi select | Single select media - click on delete Multi select media - click on delete | Media Deleted successfully and if the media is used in playlist ist showing error toast message " One or more items are used in playlist" | Pass |  |  |  |  | Pass
Media File Management | Media File Management | New Folder Button | To verify a new folder is created or not | Click on New Folder Button | New folder created successfully | Pass |  |  |  |  | Pass
Media File Management | Media File Management | New Folder Delete | To verify a new folder created, able to delete | Click on Delete option of folder | Folder deleted successfully | Pass |  |  |  |  | Pass
Media File Management | Media File Management | Update Folder | To verify a new folder created, able to update or rename | Click on Update folder option | Folder successfully updated or renamed | Pass |  |  |  |  | Pass
Media File Management | Media File Management | Select/Deselect | To verify media listed in the folder, should be able to select All, individual and Deselect All | Go to media list and check media, select, deselect | Working fine Inpute: can we add a label for sort by as we did for search? | Pass |  |  |  |  | Pass
Media File Management | Media File Management | Sort by | To verify sorting with Uploaded Date - Newest first | Applied sort by Uploaded Date - Newest first | Working fine | Pass |  |  |  |  | Pass
Media File Management | Media File Management | Sort by | To verify sorting with Uploaded Date - Oldest first | Applied sort by Uploaded Date - Oldest first | Working fine | Pass |  |  |  |  | Pass
Media File Management | Media File Management | Sort by | To verify sorting with File size - Largest first | Applied sort by File size - Largest first | Working fine | Pass |  |  |  |  | Pass
Media File Management | Media File Management | Sort by | To verify sorting with File size - Smallest first | Applied sort by File size - Smallest first | Working fine | Pass |  |  |  |  | Pass
Media File Management | Media File Management | Create Media | To verify media should be created and also able to edit in editor | Click on Create media option and Click on Editor open button | When creating media, the page redirects to the Media section, but the media cannot be selected. The “Open Editor” button is visible but not clickable. | Fail | Done |  |  |  | Fail | Facing UI issue on poster my wall page, once I click on the email, then click back to the design button.
Media File Management | Media File Management | View - Grid/List | To verify meida listed should be able to view in grid and listed views | Switching Grid to List and List to Grid view | Checked by switching grid to list view and list to grid view, found OK | Pass |  |  |  |  | Pass
Media File Management | Media File Management | Three dot menu for medias | To verify three dot menu of each media in grid view and list view | Click on three dot of media, listed at All files | Not working | Fail | Done |  |  |  | Pass | Working fine now when I click on the three dot menu, redirects to the file detail page.
Media File Management | Media File Management | Media view | To verify that listed media file should be click and view in grid and list view | Click on Media in Grid/List view - File details | Working for Grid view but not able to view file details in list. | Fail | Done |  |  |  | Pass | Able to view media file, in list view also.
Media File Management | Media File Management | Statistics | To verify Statistics of Media File Management | Calulated media for Total Files, Images, Videos, Storage Available, and Storage Used | Total Files - OK, Images - OK, Videos - OK, Storage Available - OK, and Storage Used - OK | Pass |  |  |  |  | Fail | UI issue on storage available card section. Text extending the storage available section. | Storage available and storage used are expanded compared to other cards.
Playlists | Playlist | Create PlayList | To verify that a playlist created with playlist name and description | Cliick on Create Playlist Button, Add name and description | Playlist created successfully | Pass |  |  |  |  | Fail | Playlist created successfully but how many playlists are active and how many are inactive, tags are not showing. | Once created the playlist. And again, click on the create playlist, showing the previous playlist text on the create playlist screen.
Playlists | Playlist | Duplicate Playlist | To verify that playlist duplication by clicking on three dot menu | Click on three dot of playlist, click on duplicate playlist | Playlist duplicated successfully with new name as TestPlayList Copy | Pass |  |  |  |  | Pass
Playlists | Playlist | Rename Playlist | To verify that playlist should be rename by clicking on three dot menu | Click on three dot of playlist, click on rename playlist | Successfully rename playlist | Pass |  |  |  |  | Pass
Playlists | Playlist | View History | To verify that view history of a playlist by clicking on three dot menu | Click on three dot of playlist, click on view history | Click on view histry, its redirect to Playlist histroy page and showing a table with column name Published on, Screens, Layouts, Actions. | Pass |  |  |  |  | Fail | Wrong date format showing on published on column and content detail page.
Playlists | Playlist | Delete Playlist | To verify that playlist created should be able to delete the playlist by clicking on three dot menu | Click on three dot of playlist, click on delete playlist | Click on delete playlist, playlist deleted successfully | Pass |  |  |  |  | Pass | There is a delete button available on playlist card as well.
Playlists | Playlist | Search | To verify that search should be work on playlist name and ID | Click on search bar, search by name and ID | Working fine. Inputs: how to search with ID? and correct the UI for placeholder | Fail | Done |  |  |  | Fail | Search by ID is not available
Playlists | Playlist | All Status | To verify that playlist should be listed with status Active or Inactive | Click on All status , select Active or Inactive status | Checked by active list and inactive list of playlist, for list view all the playlist are showing active status beside that filter with inactive | Fail | Done |  |  |  | Fail | Active and inactive label is not available on, Playlistcard.
Playlists | Playlist | View - Grid/List | To verify playlist listed should be able to view in grid and list views | Switching Grid to List and List to Grid view | Working fine | Pass |  |  |  |  | Pass
Playlists | Playlist | Statistics | To verify Statistics of Playlists Management | Calculated for TOTAL PLAYLISTS, ACTIVE PLAYLISTS, CONTENT ITEMS, ASSIGNED | Found OK | Pass |  |  |  |  | Fail | Active playlist card is expanded compared to other cards.
Playlists | Playlist | List view- All Playlist table | To verify playlist table in list view | Checked table of Playlist-->All Playlist | Checked and found that, duration column showng layouts count. also the sorting is not working. Inpute: We dont have layout column name in the table , required a layout column name separatly or adjust it with table. Also add Sr. column for playlist. Also in action column of list view, are we adding publish, edit, and delete option as we did in grid view. | Fail | Done |  |  |  | Fail | Need clarification this
Playlists | Playlist | List view- three dot menu- View detail | To verify that admin can view the details of playlist by clicking on view details | Click on three dot menu, Click on View details | Successfully redirect to view playlist details | Pass |  |  |  |  | Pass
Playlists | Playlist | List view- three dot menu- View History | To verify that admin can view the history of playlist by clicking on view history/Publication History | Click on three dot menu, Click on View histroy | Successfully redirect to view playlist publication history | Pass |  |  |  |  | Fail | Time format shows wrong
Playlists | Playlist | List view- three dot menu- Device menaegment | To verify that admin can view and redirect to the device managment details | Click on three dot menu, Click on Device menagement | Successfully redirect to Device management screen | Pass |  |  |  |  | Fail | Device management not available in three dot action.
Playlists | Playlist | Playlist-->Playlist History/Publication History | To verify that Publication History should be visible with correct table columns after redirect to playlist history screen. | Click on list view-Click on three dot menu-Select view history | checked with table columns Sr.,Published on,Screens, Layouts, and Actions. In action column, ON/OFF button not working. | Fail | Removed No Action Needed |  |  |  | Fail | On/Off button not available.
Playlists | Playlist | Playlist-->Device Management | To verify that device management having screen and group and its should be able to publish and schedule | Click on list view-Click on three dot menu-Select device management | Input: Can we change the option name from Device Management to Publish/Schedule Screens? Because on the breadcrumb navigation for the Device Management screen, we are showing Publish. Also we have a publish button in grid view. | Fail | Done |  |  |  | Fail | device management is not availbale to select.
Playlists | Playlist | Publish Playlists | To verify that admin can publsih the playlist by selecting screens records | Click on publish/device menagement button on grid and list view, Select screen records, Click on Publish button | Screens publish successfully and showing in publication history | Pass |  |  |  |  | Pass
Playlists | Screen Tab | Publish-->Screens records Filters | To verify that search should be work for screen records | Search by screen name | Found OK | Pass |  |  |  |  | Pending | Module not found
Playlists | Screen Tab | Publish-->Screens records Filters | To verify that admin should able to select screen records with count 5, 10, 20, 50 from drop-down | Click on Screens - Drop-down appered as 5,10,20,50 , Select any one | Found OK | Pass |  |  |  |  | Pending | Module not found
Playlists | Screen Tab | Publish-->Screens records Filters | To verify that screens should be able to search with tag names | Click on Tag, Select a tag from drop-down | Found OK | Pass |  |  |  |  | Pending | Module not found
Playlists | Screen Tab | Selected Screens | To verify that screen should be able to select and published | Click on Select records, records listed selected, Unchecked some records | Not OK. When the user unchecks the record, it is removed from the list. However, we already have a Remove option to remove records from the selected records before publishing. It should only allow records that are checked, and the record should not be removed from the list when it is unchecked. | Fail | Not A Bug |  |  |  | Pending | Module not found
Playlists | Screen Tab | Selected Screens | To verify that screen setting button is clickable | goto screen table(action column), click on setting option | Screen setting button not working | Fail | Done |  |  |  | Pending | Module not found
Playlists | Group tab | Publish-->Groups filter | To verify that search should be work for groups listed | Search by Group name | Found OK | Pass |  |  |  |  | Pass
Playlists | Group tab | Publish-->Groups filter | To verify that admin should able to select groups with count 5, 10, 20, 50 from drop-down | Click on Screens - Drop-down appered as 5,10,20,50 , Select any one | Found OK | Pass
Playlists | Group tab | Publish-->Groups filter | To verify that groups should be able to search with tag names | Click on Tag, Select a tag from drop-down | Found OK | Pass
Playlists | Group tab | Selected Groups | To verify that groups should be able to select and published | Click on Select records, records listed selected, Unchecked some records | Not OK. When the user unchecks the record, it is removed from the list. However, we already have a Remove option to remove records from the selected records before publishing. It should only allow records that are checked, and the record should not be removed from the list when it is unchecked. | Fail | Not A Bug
Playlists | Schedule Playlist | Start date and End date | To verify that user should able to schedule playlist with start date and end date | Click on Schedule button, Choose Start and End dates from calender | Please prevent to select past date as end date for scheduling the playlist, and also dont allow to select start date before end date. add a validation error message there. | Fail | Done
Playlists | Schedule Playlist | Start time and End time | To verify that user should able to schedule playlist with start date and end date | Click on Schedule button, Enter Start time and End times | Checked by entering both times and received the validation error message: "End time must be after the start time." Inputs: How will someone know which time it is (AM or PM)? Also, the error message is shown every time, even when valid input times are entered. | Fail | it's in 24hrs cycle
Playlists | Layout Edit Screen | Edit | To verify that user should be able to edit listed playlists | Click on Grid view, Click on Edit button on playlist | Successfully redirected to layout edit screen | Pass
Playlists | Layout Edit Screen | Edit | To verify Exit Button Navigation to back | Click on Edit button, Click on Exit button to back | Working fine | Pass
Playlists | Layout Edit Screen | Edit | To Verify Media tab should be selected by default | Click on Edit button | Found OK | Pass
Playlists | Layout Edit Screen | Edit | To Verify Widgets Tab Switching | Click Widgets tab - Widgets panel should open. Click Media tab - Media panel should reappear | Found OK | Pass
Playlists | Layout Edit Screen | Edit | To verify that New blank design canvas should be created | Click on New Design button | Currently, it opens PostMyWall templates. When we click on the remove (cross) button, it redirects to the Playlists dashboard, which is incorrect. It should redirect to the Layout screen so the user can click the New Design button again. | Fail | WIP
Playlists | Layout Edit Screen | Edit | To verify that Upload Media and listed in media with there categories tab | Click on Upload media | Media uploaded successfully and listed in media, but required a loader to wait for completion of upload. | Input
Playlists | Layout Edit Screen | Edit | To verify that Upload media with unsupported file format | Click on Upload unsupported media | Not allowed to upload unsupported medias | Pass
Playlists | Layout Edit Screen | Edit - Search Media | To verify that media is able to search after uploading | Search on ALL, Images, videos and folders | In the folder, when we click on a folder and search for media, the search is not working. Also, the folder icons are not shown in the preview. | Fail | Done
Playlists | Layout Edit Screen | Edit - Filter Media | To verify that media filter should be work according to image, video and folders | Filter with ALL, Images, videos and folders | Working fine | Pass
Playlists | Layout Edit Screen | Media - Drag and Drop | To verify that user should be able to Drag and drop images, videos and folder media from media panel | Media which are uploaded , Drag and Drop into zone layout | Working fine | Pass
Playlists | Layout Edit Screen | Layout Orientation - Horizontal | To veify that Canvas should display horizontal zones | Select media on canvas, Click on Horizontal button | Working fine | Pass
Playlists | Layout Edit Screen | Layout Orientation - Vertical | To veify that Canvas should display vertical zones | Select media on canvas, Click on Vertical button | Working fine | Pass
Playlists | Layout Edit Screen | Layout Orientation - Custom | To veify that Canvas should be customizable with display with Custom Canvas Size(Height and Width) | Select media on canvas, Changes width and height of media | Working fine. | Pass
Playlists | Layout Edit Screen | Layout Orientation - Rotate | To veify that Canvas should be rotate to Standard orientations are 90°, 180°, or 270° | Select media on canvas, Click on Rotate button | Working fine | Pass
Playlists | Layout Edit Screen | Layout Orientation - Full screen | To verify that Canvas should expand to full screen | Select media on canvas, Click on Full Screen button | Working fine. Input: Can we add a reset option after doing full screen. | Input
Playlists | Layout Edit Screen | Layout Orientation - Farword | To verify that Canvas should be appear to Next layout | Select media on canvas, Click on farword button | Working fine | Pass
Playlists | Layout Edit Screen | Layout Orientation - Backword | To verify that Canvas should be appear to Previous layout | Select media on canvas, Click on backword button | Working fine | Pass
Playlists | Layout Edit Screen | Add New Layout | To verify that user can create a New layout and perform all editng on canvas. | Click on New layout button | Found OK | Pass
Playlists | Layout Edit Screen | Layout Setting- Delete Layout | To verify that user can delete the layout by clicking on delete button | Goto Layout Settings, Click on delete button | Working fine | Pass
Playlists | Layout Edit Screen | Layout Setting- Copy Layout | To verify that user can copy the layout by clicking on copy button | Goto Layout Settings, Click on copy button | layouts are copied successfully but some time when we create multiple copies of layout, its stuck and display like multiple selected at onces. | Input
Playlists | Layout Edit Screen | Layout Setting- Animation Effect | To verify that user can applied Animation Effect on layout setting by clicking on Animation Effect | Goto Layout Settings, Check animation settings | Checked by appliying animation effect, but no changes found in layout preview | Fail | Done
Playlists | Layout Edit Screen | Zone Settings | To verify that zone setting works for each media uploaded | Click on Media file uploaded to the layout, Click on setting button | Checked for media zone setting, Zone Audio and Fit zone content not working, Also align UI of Zone Duration: 15s | Fail | Done
Playlists | Layout Edit Screen | Zone Settings | To verify that zone setting works for each media uploaded | Click on Media file uploaded to the layout, Click on Slide button, Click on Mute, Unmute audio and Remove | Mute and unmute not working for slide also media should be preview | Fail | Done
Playlists | Layout Edit Screen | Preview Layout | To verify that layout should be preview with media uploaded | Select layout ,Click on Preview button | Working fine | Pass
Playlists | Layout Edit Screen | Save Layout | To verify that layout should be Save with media uploaded | Select layout ,Click on Save button | Successfully saved, but when we click on the Save button, it redirects to the Playlist Dashboard. It should instead redirect to the Layout Edit screen. | Input
Playlists | Widgets | News Ticker | To verify that news ticker should be work properly with respective settings | Click on widget, click on New ticker, add name, text, font of text, direction, and speed | Input: We don’t have a font size option for the news ticker. Can we add it? Because in the preview, it is displayed with the default size. | Input
Playlists | Widgets | Web Page | To verify that web page should be work properly with respective settings | Click on widget, click on web pages, add custome param | Click on widget, click on web pages, add custome param | Fail | Done
Playlists | Widgets | Live Stream | To verify that Live stream videos should be work properly with respective settings | Click on widget, click on live stream, set forword, backword and other setting | Farword and backword not working on live stream widgets | Fail
Playlists | Widgets | Text | To verify that Text should be work properly with respective settings | Click on widget, click on text, set forword, backword and other setting | The forward and backward settings, as well as the font size, are sometimes not working for the text widget. | Fail | Done
Playlists | Widgets | Youtube | To verify that Youtube should be work properly with respective settings | Click on widget, click on youtube, set forword, backword and other setting | Working fine | Pass
Playlists | Widgets | Google Slide | To verify that Google slide should be work properly with respective settings | Click on widget, click on google slide, set forword, backword and other setting | Working fine | Pass
Playlists | Widgets | Weaather | To verify that weather should be work properly with respective settings | Click on widget, click on weather, set forword, backword and other setting | Working fine | Pass
Playlists | Widgets | Clock | To verify that Clock widgets should be work properly with respective settings | Click on widget, click on clock, set forword, backword and other setting | Working fine | Pass
Playlists | Widgets | QR generator | To verify that QR code widgets should be work properly with respective settings | Click on widget, click on QR code, set forword, backword and other setting | response 401 : {"success":false,"message":"Invalid token!","data":[]} | Fail | Done
Playlists | Widgets | AQI | To verify that AQI widgets should be work properly with respective settings | Click on widget, click on AQI, set forword, backword and other setting | Working fine | Pass
Playlists | Widgets | Google Sheets | To verify that Google sheets widgets should be work properly with respective settings | Click on widget, click on Google sheets, set forword, backword and other setting | Working fine | Pass
Playlists | Widgets | RSS | To verify that Google sheets widgets should be work properly with respective settings | Click on widget, click on RSS, set forword, backword and other setting https://rss.app/rss-feed?keyword=Technology&region=US&lang=en | Unable to load RSS feeds | Fail | Done
Playlists | Widgets | PDF | To verify that PDF widgets should be work properly with respective settings | Click on widget, click on PDF , set forword, backword and other setting | Fail to upload PDF and showing error - Setting up fake worker failed: "Failed to fetch dynamically imported module: http://147.93.155.211/assets/pdf.worker.min-GB3t0DcA.mjs | Fail
Playlists | Widgets | Power Bi | To verify that Power bi widgets should be work properly with respective settings | Click on widget, click on PowerBi, set forword, backword and other setting | The forward and backward settings, are sometimes not working for the power bi widget. | Fail
Playlists |  | Read Docs | To verify that read docs redicret to the playlist documention page | Click on edit playlist, Click on read doc button | Pending from dev team, required clearification | Pending
Playlists |  | Next Button | To verify that next button redicret to the playlist publish screen | Clcik on edit playlist, Click on next button | Redirect to the publish screen where use can publish playlist after selection | Pass
Groups Management |  | Create New Group | To verify that user can create a new group with Name, Description, Loaction, Tags | Click on Create Group button, Add Name, Description, Loaction, Tags | Select Device showing a drop-down arrow but not working. pls update the UI of Select device field where we only searching the device by name. there is not drop-down option | Fail | its As per the figma
Groups Management |  | Edit Group | To verify that group created should be editable | Click on view group-click on edit button | Found OK | Pass
Groups Management |  | Group Table | To verify that the group table has all columns correctly | Go to group management, create a group, and check table | Found OK as per the figma | Pass
Groups Management |  | Filters | To verify that group should be search with company name and group ID | Search with company name and group ID | Please update the placeholders as "Search by Company name and Group ID" as per the figma. Also search with group Id not working | Fail | Done
Groups Management |  | Filters | To verify that Group Status should be work for active, inactive and maintanace status | Filter with active, inactive and maintanace status | Working fine | Pass
Groups Management |  | Filters | To verify that user should able to filter groups with tags | Filter with tags or multiple tags | Working fine | Pass
Groups Management |  | Filters | To verify that filter unable or disabled button | Click on filter button and toggle | Working fine | Pass
Groups Management |  | Filters | To verify that reset filter and apply filter buttons are working correctly | Apply filters by selcting apply button, or reset by clicking on reset button | Found OK as per the figma | Pass
Groups Management |  | Groups-View | To verify that groups can be viewed by clicking on the View option in the group table action column. | on groups list of table, click on three dot menu and click on view option | Found OK as per the figma | Pass
Groups Management |  | Groups-View(add device) | To verify that groups can be viewed and add device | Click on view group, click on add device and Add Screens to Group | Found OK | Pass
Groups Management |  | Groups-View(Browse playlist) | To verify that groups can be viewed and browse playlist | Click on view group, click on browse playlist and schedule | Browse playlist working fine for Quick Assign | Pass
Groups Management |  | Groups-View(Browse playlist) | To verify that groups can be viewed and browse playlist | Click on view group, click on browse playlist and schedule | Browse playlist showing wrong status(playing) when we clicking on pause button of current assigned playlist | Fail
Groups Management |  | Groups-View(Browse playlist) | To verify that groups can be viewed and browse playlist | Click on view group, click on browse playlist and schedule | Skip to the next playlist in current assigned playlist not working | Fail
Groups Management |  | Groups-View(Schedule playlist) | To verify that groups can be viewed and schedule playlist | Click on view->click on schedule->Click on Playlist tab->Currnetly assigned playlist-Click on Pause and Stop buttons | Click on view->click on schedule->Click on Playlist tab->Currnetly assigned playlist-Pause and Stop buttons not working | Fail
Groups Management |  | Groups-View(Schedule playlist) | To verify that groups can be viewed and schedule playlist | Click on view->click on schedule->Click on Playlist tab->Quick assigned playlist- Click on Play now button | Showing a toast message : "Playlist assignment completed for the group." for play now button click which is wrong, expected: Playlist assigned now playing | Fail
Groups Management |  | Groups-View(Schedule playlist) | To verify that groups can be viewed and schedule playlist | Click on view->click on schedule->Click on Playlist tab->Quick assigned playlist- Click assigned button | Assigned button not working | Fail
Groups Management |  | Groups-View(Schedule playlist) | To verify that groups can be viewed and schedule playlist | Click on view->click on schedule->Click on Playlist tab->Update Schedule-Start date and end date | Please prevent selecting a past date for the start date and an end date earlier than the start date. | Fail | Done
Groups Management |  | Group Controls | To verify that Group Controls works over the app |  | This functionality depends on mobile app | pending
Groups Management |  | Group Delete | To verify that group should be delete by user | Click on delete group | Please show this toast message to the group table : "Group deleted successfully" | Fail | Done
Groups Management |  | Group Setting | To verify group setting | Click on three dot and select option group setting | Successfully redirect to group setting(pls refer TC 111 to 121 for detail testing) | Pass
Groups Management |  | Pagination | To verify that pagination works as per the Rows per page:5,10,20,50,100 | Click on Rows per page:5,10,20,50,100 | Found OK | Pass
Groups Management |  | Dublicate Group | To verify that duplication of group | Create a group with same name and detail :Name, Description, Loaction, Tags | An error message is shown: "Group name already exists," and it is not possible to add a group with the same name. input: pls show this message when user try to save & Next not at Select Device step.sometime its hsowing internal server error too. | Pass-input
Groups Management |  | Statistics | To verify that statistics of Groups Management | Checked by calculating Total Groups, Active Groups, Inactive Groups | Found OK | Pass
Help & Supports | Tickets | Create New Support Ticket | To verify that user should be able to create new support tickets or Raise Ticket | Click on New Support Ticket button and Describe your issue with form details | 1. The Description field should have a character validation limit up to 500 (or as per standard development practices) and should restrict HTML injection. 2. The Device ID field should have character validation limits. 3. The Attachment field should not allow uploading files other than the specified formats. | Fail | Points 1 and 2 are done, and 3 already works
Help & Supports | Tickets | Table | To verify that table having all the columns as per the figma | Check table columns | Select, Action are missing in table | Fail | Actions are not required in the table as discussed with Laxmi Mam
Help & Supports | Tickets | Filters | To verify that tickets raised should be searched by ticket ID | Click on search bar and Search ID | Found OK | Pass
Help & Supports | Tickets | Filters | To verify that filter should be work on Created date From to To | Select From and To dates | Pls update placeholder as dd/mm/yyyy | Fail | We are use Heroui date component so they provide their standerd and we do not modify that, so it will not be possible to display in this format. Related to this I discussed with Kunal sir
Help & Supports | Tickets | Filters | To verify that filter should be work on status | select status open, inprogress, resolved and closed | Found OK | Pass
Help & Supports | Tickets | Filters | To verify that filters should be work by selcting categorise | Click on category, select any one and apply filter | Found OK | Pass
Help & Supports | Tickets | Statistics | To verify that Total tickets, open tickets, in-progress tickets, resolve tickets, closed tickets have a correct count and also redirect to the status | Calculated by Total tickets, open tickets, in-progress tickets, resolve tickets, closed tickets counts | Found OK, but icons not match pls check UI | Fail | Done
Help & Supports | Tickets | Pagination | To verify that paginations works as per the row per page counts 5, 10, 20, 50, 100 | Click on row per page and navigate to next pages | Found OK | Pass
Help & Supports | Knowledge base | Playlist | To verify the documentation of all morix modules | Click on knowledge base section, and checked all documentation | Only playlist documentation available right now, pls take the details from BA and updates | Pending
Help & Supports | Video Tutorials |  | To verify that video tutorials should be work and able to search videos and show in the section as per th figma | Click on Video tutorials | A “Search Video Tutorials” placeholder is required, and the search functionality currently appears static, as searching is not working. Replace the “All Videos” placeholder with “All Categories”, and add category options as well. | Fail | Placeholder already has its searching also working. categories render after getting data from youtube api.
Help & Supports | Contact us |  | To verify that user should able to get all the details of contact us | Click on contact us section | Pls update the contact details as per required and figma design . Pls note figma designe has changed and updated pls check accourdigly. | Pending
Help & Supports | Download app |  | To verify that user should be able to visite and download the app by official page | Go to Download app and redirect to google app store | Pls update as per the requirements needs | Pass
Order Management | Statistics |  | To verify that client should be able to see count of Total Invoices and In-Transit | Check by calculating Total Invoices, In-Transit | Found OK | Pass
Order Management | Filters | Search | To verify that client should be able to search sale invoice by SI number | Search by SI number | Found OK | Pass
Order Management | Filters | Payment Term | To verify that client should be able to filter SI by Payment Term | Click on Payment Term and select any one | Found OK | Pass
Order Management | Filters | Payment Method | To verify that client should be able to filter SI by payment method | Click on payment method | Not working | Pass
Order Management | Filters | Status | To verify that client should be able to filter SI by status | Filter by Status | Found OK | Pass
Order Management | Filters | Created dates | To verify that client should be able to filter SI by dates created | Filter by created date | Found OK | Pass
Order Management | Reset Filters | Button | To verify that reset filter works | Click on reset filter button | Search should be also get reset on button click | Fail | Done
Order Management | Table |  | To verify that order management having all the required table columns | Checked | Found OK | Pass
Order Management | Action | View | To verify that Si should be view with details | Click on view action | Found Ok | Pass

## Morix SuperAdmin Web Applicatio
Superadmin Cred Morix web app: http://147.93.155.211:3000/ Super Admin: morix@demo.com client123 Ditributor: mohdzubair7773@gmail.com GvUel!P6,kH/
Module | Sub-module | Feature | TC & Scenario | Steps/Input data | Remarks | Priority | Severity | Testing(Pass/Fail) | Dev Remarks
Role management | Client | Add/Create Role | To verify that super admin should be able to choose role and select sub-role to add the user | Click on Client, Click on add sub-role | Role and Sub-role added successfully. 1. Input: Can we add Role Name Role Description palceholders? 2. also add a description limit upto 200 char or as per standard validation. 3. Instead of showing validation error if admin not check any permission, show message like "Please Add Permissions" 4. Aftrer clicking on Create role button, superadmin should remain in the client sub-role screen. |  |  | Input
Role management | Client | Configure Permissions | To verify that super admin can configure role persmission(Create, Edit, View and Delete and All) | Click on Client, Click on add sub-role, Check permissions by removing and adding(for specifice or All) | 1. If super admin unchecked permission for create and View then also other permission should be unchecked automatically. 2. At Client login, we dont have view and Delete option but we have permission checkbox in super admin. 3. If Super Admin access for permissions (Create, Edit, View, and Delete) is removed, or vice versa then dont allow to Create, Edit, View and Delete Client web app. |  |  | Fail
Role management | Client | Delete | To verify that super admin should be able to Delete sub-role with validation if it is not assigned | Click on Client, Click on add sub-role, Click on three dot menu and Select Delete option | Sub-role delete successfully |  |  | Pass
Role management | Client | Change to Active or Inactive | To verify that super admin should be able to Active or Inactive sub-roles | Click on Client, Click on add sub-role, Click on three dot menu and Select Change to active/inactive option | Sub-role status changed successfully |  |  | Pass
Role management | Client | Statistics-Select Role & Sub-Role | To verify that the role and sub-role client cards display both Active and Inactive counts. | Go to Cleint sub-role card, Check Active amd Inactive counts | Showing wrong count |  |  | Fail | Its for Super Admin Showing Glogal Count
Role management | Client | Save Setting and Reset to Default Buttons | To verify that Save setting and Reset to default button should be work | Checked permission, Click on Save setting, Checked permission, Click on Reset to Defaukt | Found OK |  |  | Fail | User Can only restore the setting Before the Save
Role management | Client | Sub-Role Type Scroll Button | To verify that Sub-Role Type scroll button should be work as expected | Scroll to Left and Scroll to Right | UI is not OK. The Sub-Role Type card is hidden at the rightmost and leftmost corners when scrolling. |  |  | Fail | Done
User management |  | Add User | To verify that SuperAdmin should be able to add a user with Full Name, Email, Phone Number and Selected Role | Click on Add User, Add Full Name, Email, Phone Number and Select Role | 1. If the user enters valid inputs, the error messages should be removed in the Add User form. 2. User added should be list out at the top of the table. 3. User roles drop-down should be list all roles not only distributor roles |  |  | Fail | Done
User management |  | Configure Permissions | To verify that configuration permission should be update and reset | Goto action column, Click on Edit option | Unable to edit and update permissions for roles |  |  | Fail | User On onlly update the permitions only in role management Module.
User management |  | Table | To verify that user management having all coulmn of table | Checked, Full name, Email, Role, Phone, Role, Status, Last login and action | Found OK |  |  | Pass
User management | Filters | Search | To verify that user should be search by name and Email | Search by name and email | Working OK |  |  | Pass
User management | Filters | Select Role | To verify that user should be able to filter by roles | Click on Selec role and select roles | Working OK |  |  | Pass
User management | Filters | Status | To verify that user should be able to filter by status | Click on Status , Selecd Pending, Approve and reject | Working OK |  |  | Pass
User management | Filters | Last Login date | To verify that user should be able to filter by Last login date | Select date | Working OK |  |  | Pass
User management |  | Pagination | To verify that pagination should be work as per the Rows per page and counts | Checked for rows per page: 5, 10, 20, 50, 100 | Not Working |  |  | Fail
User management |  | Statistics | To verify statistics of user management | Calculated for Total Users, Active Users, Inactive Users | Statistic should be clickable so we can get count in table |  |  | Fail | Done
User management |  | Edit User | To verify that user added should be edit and update | goto table-action-edit try to edit name, email, phone, role and config permissions | unable to update config permission which are by default set |  |  | Fail | User can only update Permition only on Role Management.
User management |  | Resend Login detail | To verify that user should be able to chnage the password by resending credentials via email | Click on resend login detail | Not working, Response: {"success":false,"message":"Client Not Found","data":[]} |  |  | Fail | Done
User management |  | Active User | To verify that user should be activated and shows status as approved | got to action column, Click on activate | Found OK |  |  | Pass
User management |  | Inactivate User | To verify that user should be inactivated and shows status as rejected | got to action column, Click on inactivate | Found OK |  |  | Pass
Order management(Distributor) | Purches | Create New RFQ and Send | To verify that Create New RFQ created with fields Name, Size, Color, Decription, HSN code, Delivery Time, Qty and send | Click on Add item , New RFQ created | A new RFQ is created, but the Add Item form does not include Size and HSN code fields. Also, when submitting an empty form, Product, Color, Quantity, and Delivery Time are highlighted in red with error messages. Please add a description char limit |  |  | Fail | Done
Order management(Distributor) | Purches | Created New RFQ listing | To verify that Created new RFQ should be listed in the product summary | Create New RFQ, Click on back button, Revisite Create New RFQ page | The newly created RFQ is not found in the Product Summary list after revisiting the Create RFQ page; it shows "No data found." Note, user not deleted RFQ. |  |  | Fail | In dev side, it is working fine, so please Retest
Order management(Distributor) | Purches | RFQ Information | To verify that RFQ Information auto generate | Click on add item and create new RFQ | RFQ Number generate with date and RFQ number after creation of RFQ |  |  | Pass
Order management(Distributor) | Purches | Product Summary | To verify that product summary having Name, Size, Color, Decription, HSN code, Delivery Time, Qty amd Action- Duplicate and Delete | Check by creating new RFQ | The following fields are not found in the Product Summary: Size,HSN Code, and Action (Duplicate). Also Qty field UI not looking good. |  |  | Fail | Done
Order management(Distributor) | Purches | RFQ-Table | To verify that RFQ table should be include Sr No., RFQ date, RFQ no., Buyer name, Buyer type, Product summary, Total QTy, Status , action(Edit, View, Download) columns | Click on View RFQ-table | Not showing buyer full name in the table, also wrong buyer name displayed. User having name Test User aa but in table showing Zubair. Pls add Sr No columns also in RFQ table. Note: Buyer name and Buyer type is it in figma, so i tested by using figma |  |  | Fail | Getting buyer details from the API is wrong, so we need to make a change in backend side
Order management(Distributor) | Purches | RFQ-statistics | To verify that RFQ statistics | Calculated by Total rfqs Pending RFQs, Rejected RFQs,Quotations Generated count | Found OK but also required clickable |  |  | Fail | Done
Order management(Distributor) | Purches | Filter - RFQ - Search | To verify that search work on RFQ number, buyer name | Click on search by buyer name, and RFQ number | Placeholder not found, |  |  | Fail | Done
Order management(Distributor) | Purches | Filter - RFQ - date | To verify that In the RFQ date filter, do not allow selecting a past date for the From field and a future date for the To field. | Select dates from Calendar | Do not allow selecting a future date for the From field and a past date for the To field. Also, add placeholders so users can clearly identify which field is From and which is To. |  |  | Fail | Done
Order management(Distributor) | Purches | Filter - RFQ - Status | To verify that staus should be work for drop-down options | Filter status with pending review, quatation generated, rejected RFQ | Found OK |  |  | Pass
Order management(Distributor) | Purches | Filter - RFQ - Export selected button | To verify that export selected button should be work and selected RFQ exported | Click on export selected button | Not working, |  |  | Fail | Done
Order management(Distributor) | Purches | Reset Filter Button | To verify that reset filter button should be reset all fillters | Click on reset filter button | Seaarch keywords not reset on click reset filter |  |  | Fail | Done
Order management(Distributor) | Purches | Edit RFQ | To verify that user can edit RFQ | Click on edit from action column | The following fields are not found in the Product Summary for edit RFQ: Size, HSN Code. And when we click on Update button its shows Item 1: Delivery Time should be greater than 0.error message. also Qty UI not looks good |  |  | Fail | Done
Order management(Distributor) | Purches | View RFQ | To verify that user can view RFQ | Click on view from action column | The following fields are not found in the Product Summary for View RFQ: Size, HSN Code. also Qty UI not look OK. if we are only perform action view then dont need to show actions menu. Pls Check UI of status, Inside view, status color should be match with table-status column color of RFQ. Icons are not match pls update it. Note: Do it same for Super Admin and overl all places |  |  | Fail | Done
Order management(Distributor) | Purches | Download RFQ | To verify that RFQ should be downloaded | Click on Download from action column | Not implemented |  |  | Fail
Order management(Distributor) | Purches | Create New PO-without Quatation | To verify that user can Generate Purchase Orders without quatation | Goto Quick Actions-Click on Create new PO | size is missing in the Create PO |  |  | Fail | Done
Order management(Distributor) | Purches | Product Summary | To verify that Created Po having the product summary including: name, size, color, description, HSN code, Delivery time, Qty, Unit price, Discount, GST, Total amoount, Action-Duplicate and Delete | Goto Quick Actions-Click on Create new PO - Check Product summary | size is missing in the product summary |  |  | Fail | Done
Order management(Distributor) | Purches | PO Information | To verify that PO info should have number and PO date auto generated | Check PO Information | Pls remove auto generated keyword from PO number or add a space between them |  |  | Fail | Done
Order management(Distributor) | Purches | Create PO button | To verify that user can create PO by clicking on create PO button | Add Item- click on Create PO button | Validation error while creating PO by clicking on Create PO button. Response: { "success": false, "message": "Validation error", "data": { "errors": { "quotationId": [ "The quotationId field is required." ], "buyerId": [ "The buyerId field is required." ], "buyerName": [ "The buyerName field is required." ] } } } |  |  | Fail | Done
Order management(Distributor) | Purches | Duplicate PO | To verify that User can duplicate created PO | Click on action-duplicate PO | Found Ok |  |  | Pass
Order management(Distributor) | Purches | Delete PO | To verify that user can delete the PO listed | Click on action-delete PO | Found OK |  |  | Pass
Order management(Distributor) | Purches | Created PO listing | To verify Created Po should be listed in product summary | Created PO, goto back button, again visite create PO | The created PO is not shown after revisiting it; it displays “No results found.” |  |  | Fail | Done
Order management(Distributor) | Purches | Create PO with Quatation | To verify that user can Generate Purchase Orders with quatation | Goto Quick Actions-Click on Create new PO | size is missing in the Create PO |  |  | Fail | Done
Distributor Management(SAdmin) | Purches | Add Distributor | To verify that admin can add distributor with Profile detail, Billing & shipping detail and team management. | Click on add, fill out the details for Profile detail, Billing & shipping detail and team management. | Profile Details: PAN number is mandatory, and Udyam Number is also mandatory. Error validation messages should be removed when the user enters valid inputs. Team Management: Note: UI does not match with Figma. On clicking the Submit button, if any field has an issue (e.g., “Email already exists”), it should be shown as a toast message so the user can edit it at the final stage. |  |  | Fail | Done
Distributor Management(SAdmin) | Purches | Listing | To verify that distributor added should be listed at the top of the table | Check distributor table | currently latest added distributors are at the bottom of the listing |  |  | Fail | Done
Distributor Management(SAdmin) | Purches | Edit Distributor | To verify that the admin can edit and update a distributor, and that the distributor can log in using the resent credentials. | Go to action column, click on edit button. | Distributor edit and updated successfully and received new credentails and login |  |  | Pass
Distributor Management(SAdmin) | Purches | View Distributor | Verify that admin can view distributor details with Profile detail, Billing & shipping detail and team management. | Go to action, click on view button | Profile Details Adress , City, Country, Udhyam, PAn number are missing in distributor detail |  |  | Fail | Done
Distributor Management(SAdmin) | Purches | Filters - Search | To verify that admin can search distributor by company name and email | Search by company name and email | Not working with comapnay name |  |  | Fail | Done
Distributor Management(SAdmin) | Purches | Filters | To verify that admin can filter by roles | Filter by role | Found OK |  |  | Pass
Distributor Management(SAdmin) | Purches | Filters - Status | To verify that admin can filter distributor by status | Filter by status active and inactive | Found OK |  |  | Pass
Distributor Management(SAdmin) | Purches | Filters - City | To verify that admin can filter distributor by city | Filter by city | Not working |  |  | Fail | Done
Distributor Management(SAdmin) | Purches | Filters - Dates | To verify that admin should be able to filter distributor by dates | Pick a date From and TO | Do not allow selecting a future date for the From field and a past date for the To field in the calendar. Also, please update the placeholder to the dd/mm/yyyy format and add a clear placeholder/label for the calendar so users can understand whether it refers to the Added Date or Last Updated Date. Additionally, the calendar picker is not working. |  |  | Fail | Done
Distributor Management(SAdmin) | Purches | Filters - Parent Distributor | To verify that parent distributor should be workable | Select Parent distributor | No option found for select paresnt distributor |  |  | Fail | As discussed with Kunal sir, this field does not require.
Distributor Management(SAdmin) | Purches | Reset Filter Button | To verify that on reset filters , filters should be clear | Click on reset filter button | search bar not reset on reset button |  |  | Fail | Done
Distributor Management(SAdmin) | Purches | Export selected | To verify that admin should be able to export selected distributor | Click on export selected button | Not working |  |  | Fail | Done
Distributor Management(SAdmin) | Purches | Resend email invite | To verify that admin should be able to resend emailinvite to reset credentials of distributor | Click on resent email invite | Crednetials received via email and login successfully: Username: mohdzubair7773@gmail.com Password: arv)_N_TNst: |  |  | Pass
Distributor Management(SAdmin) | Purches | Statistics - Distributor Manage. | To verify that Total Distributors,Total Sub-Distributors,Active Distributors,Inactive Distributors,Active Sub Distributors. having a correct count | Check by calculating Total Distributors,Total Sub-Distributors,Active Distributors,Inactive Distributors,Active Sub Distributors, Inactive sub distributor | Total Distributor should be total of distributor and sub distributor |  |  | Fail | Statistics clickable done by the front-end side count is coming from the backend side, so pending from the backend
Order management(SA) | Sales | View RFQ | To verify that View RFQ detail after creating RFQ from distributor side | Checked, status is Pending review, ibyer details RFQ information and Product Summary | Checked, status is Pending review, in Buyer details- Udaym number and GST number not shown |  |  | Fail | These details are not coming from the API, so they are related to discussed with Abdul
Order management(SA) | Sales | Edit-Quatation | To verify that SA can edit Quotation after status change from view RFQ | checked edit quatation | Found OK input: can we add select in product summary table also for edit quatation to delete multiple selections. |  |  | Pass
Order management(SA) | Sales | Download -Quatations | To verify that SA should be able to diownload selected quatation by clicking on action-download | goto action and click on download button option | Not working |  |  | Fail
Order management(SA) | Sales | Filters-Quatations | To verify that search works for quatation listed | Search with quatation number | Found OK |  |  | Pass
Order management(SA) | Sales | Filters-Quatations | To verify that quatation filter by buyer name , buyer type works for quatation listed | Filter by buyer name and Buyer type | Found OK |  |  | Pass
Order management(SA) | Sales | Filters-Quotations | To verify that quatation filter by created dates(From to To) works for quatation listed | Filter by created dates | Not working. Also, update the placeholder format of dates to dd/mm/yyyy and correct the date selection logic. From: should not allow selecting dates after the To date. To: should not allow selecting dates before the From date. |  |  | Fail | Done
Order management(SA) | Sales | Apply and Reset Buttons-Quatations | To verify that apply and reset button should be work for filters applied | Checked by applying and reseting filters | Search should be reset by cliking on reset filters |  |  | Fail | Done
Order management(SA) | Sales | Quatations-Statistics | To verify that quatation statistic as per the status Total, Sent, Accepted, Rejected | Calculated by Total, Sent, Accepted, Rejected counts | Found OK |  |  | Pass
Order management(SA) | Sales | Create New Quatation | To verify that SA should be able to Create New Quotation by clicking on created quatation button and Sent to distributor | click on create new quatation | Found OK |  |  | Pass
Order management(Distributor) | Purches | Statistics-Quatation | To verify that quatation statistic as per the status Total, Sent, Accepted, Rejected | Calculated by Total, Sent, Accepted, Rejected counts | Not OK, Pls also update icons, |  |  | Fail | Count is getting the correct icons, will update
Order management(Distributor) | Purches | View-Quatation | To verify that distributor can view quataion with details -Quotation Information, Porduct summaryand perform action Reject and Accept quataion and generate PO | Click on view quatation after sending by SA | Found OK |  |  | Pass
Order management(SA) | Sales | View PI | To verify that view PI having the details -Proforma Invoice (PI) Information, Buyer details and Product Summary | Click on View PI | In Buyer details- PAN number is missing |  |  | Fail | Dev side, it is working fine. Note: If the PAN number is not added in the buyer's details, then it will not be visible in that field
Order management(SA) | Sales | Create Sales Invoice | To verify that SA should be able to Create Sales Invoice | Creating Sales Invoice for SI number | 1. Adding Buyer details- PAN number should be also auto fill, which is not shown.also In Buyer details- PAN number is missing. 2. Delivery Challan Information, GRN Information( GRN Date), RMA Information(RMA Date) and LR Information correct the date formate DD/mm/yyy. 3.Showing validation error - Each item must have scanned SKU count exactly equal to Qty. 4. Also required size in add item |  |  | Fail | Done
Order management(SA) | Sales | View Invoice - Sales Invoice & Payments- Statistics | To verify that View Invoice statistics with SI sent, Shipment generated, cancel SI, Total Invoice value, Total Outstanding, Payment received | Calculated by SI sent, Shipment generated, cancel SI, Total Ivoice value, Total Outstanding, Payment received count. Also statistic should be clickable | Not OK |  |  | Fail | Done
Order management(SA) | Sales | Sales Invoice & Payments- Filters | To verify that admin can search SI number | Search by Si number | Found OK |  |  | Pass
Order management(SA) | Sales | Sales Invoice & Payments-Filters | To verify that admin can filter by Buyer name and buyer type | Filter by buyer name and buyer type | When filtering by Buyer Type, the buyer type is not shown in the table column. The Buyer Name filter should work for exact matches |  |  | Fail | Done with UI side, buyer type not coming from backend side.
Order management(SA) | Sales | Sales Invoice & Payments-Filters | To verify that admin should be able to filter by status | Filter by status sent, paid, partiallt paid, cancelled | Filter by status sent, paid, partiallt paid, cancelled |  |  | Pass
Order management(SA) | Sales | Sales Invoice & Payments-Filters | To verify that In the Sales invoice & Payment date filter, do not allow selecting a past date for the From field and a future date for the To field. | Filter by created dates | Not Working Also update the dates formate as dd/mm/yyyy
Order management(SA) | Sales | Sales Invoice & Payments-Filters | To verify that reset filter button should be reset all fillters | Click on reset filter button | Search keywords also get reset |  |  | Fail | Done
Order management(SA) | Sales | Sales Invoice & Payments-Reset Filter button | To verify that selected SI should be downloaded | Click on export selected button | Not implemented |  |  | Fail | Done
Order management(SA) | Sales | Sales Invoice & Payments- table | To verify that all the respective data columns shouldbe display for Sales Invoice & Payments table | Checked Sales Invoice & Payments- table | Buyer type and sales person name data not diplay in the table columns |  |  | Fail | Done with UI side, buyer type not coming from backend side.
Order management(SA) | Sales | Edit SI-Edit Sales Invoice | To verify that SA should be able to edit the SI | go to action-edit SI | Sales Invoice (SI) Information: PI date is not shown. Product Summary: Size is not displayed. Delivery Challan Information: Should be auto-filled. Package Information: Should be auto-filled. GRN – GRN Information: Should be auto-filled. RMA – RMA Information: Should be auto-filled, and the Product Summary (Product Name, Size, Color) should also be displayed. Payment Tracking: Reference Number, Balance Amount, and Remarks are not shown in the table. LR Information- should be auto fill. Serial No: Product Name, Size, Color, and HSN Code should be displayed in the table. |  |  | Fail | WIP
Order management(SA) | Sales | View Sales Invoice | To verify that SI should be include details-Sales Invoice (SI) Information,Buyer details ,Tracking Details, Product Summary | goto View SI | Sales Invoice (SI) Information: PI date is not shown. Product Summary: Size is not displayed. Delivery Challan Information: Should be auto-filled. Package Information: Should be auto-filled. GRN – GRN Information: Should be auto-filled. RMA – RMA Information: Should be auto-filled, and the Product Summary (Product Name, Size, Color) should also be displayed. Payment Tracking: Reference Number, Balance Amount, and Remarks are not shown in the table. LR Information- should be auto fill. Serial No: Product Name, Size, Color, and HSN Code should be displayed in the table. |  |  | Fail | WIP
Order management(SA) | Sales | Generate Shipment Note | To verify that generating shipmenet note should be include details: Shipment Information, Buyer details, and Package Information | Goto shipment note - add detail: Shipment Information, Buyer details, and Package Information | Package Information- unable to attached - CC attached(showing disabled) After generating Shipmenet note- user should be redirect to Shipment Tracking page. |  |  | Fail | Done
Order management(SA) | Sales | Generate Shipment Note- View | To verify that shipmenet note view should be include details: Shipment Information, Buyer details, and Package Information | Goto shipment note - add detail: Shipment Information, Buyer details, and Package Information-go to view | UI issue- status color in shipment note -view not match. LR Information should be auto generated. CC attach is disabled in view too. Input- Are we uplaoding LLR images in view of shipment note |  |  | Fail
Order management(SA) | Sales | Generate Shipment Note- Edit | To verify that shipmenet note vedit should be include details: Shipment Information, Buyer details, and Package Information | Goto shipment note - add detail: Shipment Information, Buyer details, and Package Information-go to edit | LR Information: Uploading images should have validation or limits, and only allowed formats (images and PDFs) should be permitted. Also, verify whether the status is changing from Pending_LR to LR_Received on edit and update of Shipment Notes. The status should change only when the Generate Challan button is clicked. Pls check also After clicking Save & Update in Edit Shipment Note, the user no longer has the Edit Shipment Note option available in the Action column. |  |  | Fail
Order management(SA) | Sales | Generate Shipment Note- Print | To verify that shipmenet note should be print | Goto action column- click on print | Not implemeneted |  |  | Fail
Order management(SA) | Sales | Filter- Shipment tracking - search | To verify that search should be work with shipment no and buyer name | Goto search bar and search with shipmenet no and buyer name | Search not working for exact match. Update the placeholder according to search option
Order management(SA) | Sales | Filter- Shipment tracking - Status | To verify that filter should be work with shipment status | Filter with shipment status | working fine but UI is not OK, drop-down expanding too long |  |  | Fail
Order management(SA) | Sales | Filter- Shipment trackingv-buyer name | To verify that filter should be work with buyer name | Filter with buyer name | Same logo for buyer name as we add for transport name. Scroller may be required if list of buyer is too long to scroll. |  |  | Fail
Order management(SA) | Sales | Filter- Shipment trackingv-Dates | To verify that filter should be work with dates | Filter with dates | Do not allow selecting a future date for the From field and a past date for the To field in the calendar. Rename the date filter to Shipment Dates or add a label so users can clearly understand it. |  |  | Fail
Order management(SA) | Sales | Filter- Shipment trackingv-Transporter name | To verify that filter should be work with Transporter name | Filter with trasnporter name | working fine but UI is not OK, drop-down expanding too long |  |  | Fail
Order management(SA) | Sales | Reset Filter Button-Shipment tracking | To verify that reset filter button shoult be reset all filters | Click on reset filter button | Search keywords which is search shoud be reset too |  |  | Fail
Order management(SA) | Sales | Reset Filter Button-Export Selected | To verify that export selected button should be work and selected shipments exported | Clickon export selected button | Not working |  |  | Fail
Order management(SA) | Sales | Shipment tracking-Table | To verify that shimpnent tracking table should have all the data columns | Checked each column with figma | Found OK |  |  | Pass
Order management(SA) | Sales | Shipment tracking-Pagination | To verify that pagination should be work wirh row per page and count | Check by row per page as: 5, 10, 20, 50, 100 and count | Not working |  |  | Fail
Order management(SA) | Sales | Shipment tracking-Statistics | To verify that statis of shiment tracking should be correct count with Total shipments, Pending LR, LR received | Check by calculating Total shipments, Pending LR, LR received | Not Ok, Pls check UI also Icons not match. |  |  | Fail
Order management(Distributor) | Purches | Filters-Quatation-Search | To verify that search shoukd be work with quatation Number | Search by Quatation number | Found OK |  |  | Pass
Order management(Distributor) | Purches | Filters - Quatation- Status | To verify that filter should be work with Status | Filter by status sent , accepted and rejected | Found OK |  |  | Pass
Order management(Distributor) | Purches | Filters-Quatation-Dates | To verify that in the quatation created date filter, selecting a past date for the From field and a future date for the To field should not allowed. | Filter by created dates | Not working, |  |  | Fail | WIP
Order management(Distributor) | Purches | Reset Filter Button-Quatations | To verify that reset filter button should be reset all fillters | By clicking on reset button | Search bar keywords not get reset |  |  | Fail
Order management(Distributor) | Purches | Export selected Button-Quatations | To verify that export selected button should be work and selected quatations exported | By clicking on export button | Not working |  |  | Fail
Order management(Distributor) | Purches | View-Quatations | To verify that click on view quatation should be view details like Quotation Information, Product Summary | Go to action-click on view quatation | Found OK |  |  | Pass
Order management(Distributor) | Purches | Download -Quatations | To verify that selected Quatations should be downloaded | goto action-click on download | Not implemented |  |  | Fail
Order management(Distributor) | Purches | Table-Quatations | To verify that quatation tabel should be match with figma | Checked quatation table columns | Sr. No columns is missing in the table. Status for sent and accepted color should be match in the table and view quatations. Inpute: are we adding sorting for table columns |  |  | Fail
Order management(Distributor) | Purches | Generate GRN | To verify that distributor should be able to generate GRN after generating invoice from SA | Distributor try to generate GRN by clicking on generate GRN button with detail GRN Information, Buyer details, Product Summary | The Contact Number and Email fields require proper validation error messages. Validation is required for uploading attachments, including a limit on upload size. Only supported media formats should be visible for selection; unsupported formats should not appear in the file explorer. If a user attempts to upload unsupported media, a validation message should be shown. After generating GRN, user should be redirect to Goods Receipt Notes listing page. |  |  | Fail
Order management(Distributor) | Purches and Sales | Generate GRN-Table | To verify that GRN table should be contain all the required data columns following figma | checked by figma | LR no, LR date, Transporter name data are missing in table after generating GRN |  |  | Fail
Order management(SA) | Sales | View GRN | To verify that generated GRN should be approved or reject or Resend by SA and View | Check by click on view GRN | The uploaded attachment should display only the uploaded media, and the upload media option should not be shown in the View GRN screen. Seller Approved Quantity and Rejected Quantity should be editable, but they are currently not working. |  |  | Fail
Order management(SA) | Purches and Sales | Edit GRN | To verify that generated GRN should be editable | Checked by generating GRN | input: how to edit GRN bcz we dont have option for that? |  |  | Input
Order management(Distributor) | Purches | Filters-GRN-dates | To verify that user can filter by dates start and end | Checked by adding date from calendor | Do not allow selecting a future date for the From field and a past date for the To field in the calendar. Rename the date filter to created Dates or add a label so users can clearly understand it. Update formate of dates as dd/mm//yyyy |  |  | Fail
Order management(Distributor) | Purches | Filters-GRN-Transporter name | To verify that user can filter by transporter name | filter by transporter name | Transporter name list not shown, also UI for Drop-down should not extra expand |  |  | Fail
Order management(Distributor) | Purches | Filters-GRN-status | To verify that user can filter by status | Filter by status Pending, Accepted, Rejected | Found OK |  |  | Pass
Order management(Distributor) | Purches | Filters-GRN-LR date | To verify that user can filter by LR dates | Filter by LR dates | Not Working |  |  | Fail
Order management(Distributor) | Purches | Filters-GRN-Search | To verify that user can search by GRN numbers | Search by GRN number and Buyer name | Pls update the placeholder, and There is no buyer name column in GRN table. Also pls check UI of Whole components of Filter GRN |  |  | Fail
Order management(Distributor) | Purches | Statistics-GRN | To verify that statistic of GRN with Total GRN, Pending GRN, Accept GRN, Rejected GRN counts | Calculated by Total GRN, Pending GRN, Accept GRN, Rejected GRN count | Statistics should be redirect on click to respective status with correct count listing. Also check for Icons not match as per design |  |  | Fail
Order management(Distributor) | Purches | GRN-Exported selected | To verify that GRn should be exported on exported button click | Click on exported button | Not Working |  |  | Fail
Order management(Distributor) | Purches | GRN-reset filter button | To verify that reset filter button should be reset all fillters | Click on reset filter button | Search also get reset |  |  | Fail
Order management(SA) | Sales | Generate RMA | To verify that SA can generate RMA with details RMA Information, Buyer detail, Product summary | goto View RMA, generate RMA | In RMA Information, for auto fill fields should be shows in gray. Show error validation message if user generate without mandatory fields(GRN number, Si number). Buyer details- Contact person, GST number, Udyam number fields should be editable. Product summary-size and color not shown |  |  | Fail
Order management(SA) | Sales | RMA-table | Verify that RMA table should be contain table of columns with data: RMA Number,Created Date,GRN Number,GRN Date,SI Number,SI Date,LR Number,LR Date,Quantity,Status,Actions(Print, view, download) | Checked by figma designe | Found OK |  |  | Pass
Order management(SA) | Sales | RMA-KPI | To verify KPIs of RMA with Total RMA, pedning, Accepted, rejected counts | Checked for statistics of RMA with Total RMA, pedning, Accepted, rejected | Count is OK, Icons not match as per designe KPI should be clickable and redirect to respective status |  |  | Fail
Order management(SA) | Sales | Filter-RMA-Search | To verify that search should be work with RMA number |  | Search with RMA number not working. inpute: also required a placeholder |  |  | Fail
Order management(SA) | Sales | Filter-RMA-status | To verify that filter with status should be work for RMA list |  | Filtering by Status is working fine; however, please rename Rejected GRN to Rejected for RMA. |  |  | Fail
Order management(SA) | Sales | Filter-RMA-dates | To verify that filter with strat and end dates should be work for RMA list |  | Start Date and End Date filters are not working. Also, add labels so users can understand which dates to use for searching.
Order management(SA) | Sales | Filter-RMA-LR number | To verify that filter with strat and end dates should be work for RMA list
Order management(SA) | Sales | Filter-RMA-LR dates | To verify that filter with strat and end dates should be work for RMA list