## jokham_2025-12-05_03.00pm.csv
Key | Issue Type | Summary | Status | Assignee | Web/Mobile app | Production Status | QA remarks
JOK-7 | Issue | When adding a customization order, after selecting the salesperson, the app exits automatically. | To Do | Vendor | Mobile app |  | Done
JOK-8 | Changes | In Customized and Repair orders, media uploaded using the camera should be able to be cropped and upload | Done | Vendor | Mobile app
JOK-9 | Changes | Add two new fields in 'Additional Details' section for 'Add new customized orders' | Done | Vendor | Mobile app
JOK-10 | Issue | Sample Name and Sample Gr. Wt. are not shown in the Customized Order Edit screen | Done | Mohammad Zubair | Mobile app
JOK-11 | Issue | Rename Sample Name and Sample Gr. Wt. to Customer sample name and Customer Sample gr wt | Done | Mohammad Zubair | Mobile app
JOK-12 | Issue | Customized Order 'Note' UI does not match the Repair Order 'Note' UI, please make them similar | Done | Mohammad Zubair | Mobile app
JOK-13 | Issue | Order card expands on click but doesn’t close when switching filters. It should reset and close automatically | Done | Vendor | Mobile app
JOK-39 | Issue | Stone weight(St wt) is showing a default value of 0.004 in the Customized Order details | To Do | Vendor | Mobile app
JOK-37 | Issue | Order Actions Filter - wrong status filter | In Progress | Vivek Singh | Web app
JOK-14 | Issue | In Gemstone, the Certificate Name is not showing as selected in the Edit Customized Order screen | Done | Vendor | Mobile app
JOK-15 | Issue | placeholders for Customer Sample Name and Customer Sample Gr Wt are hidding | Done | Mohammad Zubair | Mobile app
JOK-40 | Changes | Update Diamond, Polki, and Stone weight input fields to allow right-to-left entry (e.g., 00.001) | To Do | Vendor | Mobile app
JOK-47 | Changes | Remove invalid character validation from Note field to allow multi-language input-mobileApp | Done | Vendor | Mobile app
JOK-52 | Issue | Do not allow the space when entering order number in mobile app for customized order/repair order | Done | Vendor | Mobile app
JOK-54 | Changes | Note' added by the salesperson and Branch manager should be scrollable | To Do | Vendor | Mobile app
JOK-36 | Issue | Pending actions logic is wrong in salesperson | In Progress | Vivek Singh | Web app
JOK-6 | Changes | Phone number should come below the customer name or at the right side | To Do | Vendor | Mobile app
JOK-53 | Changes | Customer should not be editable for other branch | To Do | Vendor | Mobile app
JOK-5 | Issue | when the app is uninstalled, all saved credentials should be cleared | To Do | Vendor | Mobile app
JOK-50 | Issue | Data does not appear on the dashboard and in the customized order section of the app-backend | Done | Mohammad Zubair | Mobile app
JOK-17 | Issue | Updated Dashboard order data in Backoffice | Done | Vivek Singh | Web app | Done
JOK-20 | Issue | Salesperson remark is not visible in the vendor PDF print | Done | Vivek Singh | Web app | Done
JOK-19 | Changes | Vendor code field should be editable for both Admin and BO | Done | Vivek Singh | Web app | Done
JOK-28 | Issue | Vendor not found in Backoffice after adding from Super Admin | Done | Vivek Singh | Web app | Done
JOK-29 | Changes | Removed the email ID mandatory validation from the email field of vendor | Done | Vivek Singh | Web app | Done
JOK-22 | Changes | Add two new fields in ‘Additional Details’ section for ‘Add new customized orders’ | Done | Vivek Singh | Web app | Done
JOK-27 | Discarded | Remark option required on order status – returned to Branch | To Do | Vivek Singh | Web app
JOK-33 | Issue | Stone weight showing by default a value 0.004 in the order print sheet | Done | Vivek Singh | Web app | Done
JOK-35 | Issue | Notes only half is visible in order view | Done | Mohammad Zubair | Web app
JOK-38 | Changes | Popup to view and download media items | To Do | Vivek Singh | Web app
JOK-41 | Changes | Update Diamond, Polki, and Stone weight input fields to allow right-to-left entry (e.g., 00.001) | Done | Mohammad Zubair | Web app
JOK-42 | Changes | Rename status 'Mark as Delivered' to Approved and Ready to Delivered | Done | Mohammad Zubair | Web app
JOK-43 | Discarded | Remarks are required for Back Office status updates when the order status becomes ‘Sent to Back Office' | To Do | Vivek Singh | Web app
JOK-44 | Changes | Branch Manager name is not visible in the order view- Changes in order details | Done | Vivek Singh | Web app
JOK-25 | Issue | Image, video, audio links do not appear in PDF after downloading | Done | Vivek Singh | Web app
JOK-26 | Changes | Blank fields should not appear in the PDF print-out | Done | Vivek Singh | Web app | Done
JOK-30 | Changes | Add Item names in customized order: PLATINUM BALI PLATINUM BANGLE PLATINUM BRACELET PLATINUM CHAIN PLATINUM EARRING PLATINUM FINGERING PLATINUM KADA PLATINUM NECKLACE PLATINUM NOSE PIN PLATINUM PENDANT MM PT CHAIN MM PT EARRING MM PT BRACELET MM PT KADA MM PT FINGERING MM PT NECKLACE MM PT PENDANT | Done | Vivek Singh | Web app | Done
JOK-46 | Changes | Remove invalid character validation from Note field to allow multi-language input | Done | Vivek Singh | Web app
JOK-48 | Changes | Changes- Add item names in customized order item list | Done | Mohammad Zubair | Web app
JOK-51 | Issue | Incorrect Status Applied to Previous Order After Cancel Action- Order status get updated automatically | Done | Mohammad Zubair | Web app
JOK-55 | Issue | Disable Update Button Until Status is Selected | In Progress | Vivek Singh | Web app
JOK-56 | Changes | Audit Log should display the actual data not the payload. | To Do | Vivek Singh | Web app
JOK-34 | Issue | Filter by Role not working correctly in Admin | Done | Vivek Singh | Web app
JOK-24 | Changes | Update and rename the branch names | Done | Vivek Singh | Web app
JOK-31 | Changes | Required Same email address for different back offices users | Done | Vivek Singh | Web app
JOK-32 | Changes | Admin password change – make admin can change the password for users | Done | Vivek Singh | Web app | Done
JOK-49 | Changes | Unable to change the password for users in the Admin Panel → User & Roles | Done | Vivek Singh | Web app
| Changes | Update and rename branch name as : not NJT --> NJ1 Not HQ --> HO- | Done | Vivek Singh | Web app | Done
| Changes | The “Email already exists” issue has been resolved by allowing the same email address for different back offices | Done | Vivek Singh | Web app | Done
| Changes | Add Gemstone name in customized order: GEMSTONE ALEXANDRITE GEMSTONE AMETHYST GEMSTONE CATSEYE GEMSTONE CORAL GEMSTONE EMERALD GEMSTONE FIROZA GEMSTONE STONE GEMSTONE GEMSTONE GUNMETAL STONE GEMSTONE LAPIS GEMSTONE MOISSANITE GEMSTONE ZIRCON GEMSTONE GOMED GEMSTONE HAKIK GEMSTONE LAJWANTI GEMSTONE MOONSTONE GEMSTONE MOTI GEMSTONE NAVGRAHA GEMSTONE NEELAM GEMSTONE NILI GEMSTONE ONYX GEMSTONE OPAL GEMSTONE PERIDOT GEMSTONE PUKHARAJ GEMSTONE RUBY GEMSTONE RUDRAKSHA GEMSTONE TIGER GEMSTONE TOPAZ | Done | Vivek Singh | Web app | Done